## Sheet1
Franklin Township Community School Corporation
Preliminary Construction
Planning Schedule
ACTIVITY |  | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
|  | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Est. Cost
Bunker Hill Elementary Ventilation Project | $1.8 Million | bar: 2021 S to 2023 A
Acton Elementary Ventilation Project | $2.5 Million | bar: 2021 S to 2022 D
Arlington Elementary Ventilation Project | $1.3 Million | bar: 2021 N to 2023 A
Kitley Intermediate School Project | $16 Million | bar: 2021 A to 2023 J
Edgewood Intermediate School Project | $18 Million | bar: 2021 D to 2023 D
New Elementary School | $35 Million | bar: 2021 S to 2024 M
Transportation Center Project | $2.3 Million | bar: 2021 A to 2023 J
FCHS Addition | $18 Million | bar: 2022 M to 2024 D
Thompson Crossing Roof Project | 275000 | bar: 2022 J to 2022 A
South Creek Roof Project | 700000 | bar: 2022 J to 2022 A
Legend:
Design
Bidding/Contract/Administration
Material Procurement
Construction