## Sheet1
Franklin Township Community School Corporation
High School Classroom Addition Schedule, Phase I
| 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
| J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Project Planning | bar: 2022 M to 2022 J
Board Meeting | bar: 2022 J
Board Meeting | bar: 2022 J
Schematic Design & Estimating | bar: 2022 A to 2022 O
Design Development Design & Estimating | bar: 2022 O to 2022 D
Final Design & Estimating | bar: 2022 D to 2023 J
Bidding | bar: 2023 J
Contract Approval & Administration | bar: 2023 F to 2023 M
Permitting & Material Procurement
Construction | bar: 2023 M to 2024 S
Move-In & Occupancy | bar: 2024 S to 2024 O
2022-10-26